## Sheet1
8x8 ¦ Design Tracker
01 Unauthenticated Prospect Experience (Priya, PRM) | [5 empty] | Audience access |  | Brand UI
Number | Page | Workstream | DRI | Content Due Date | Content Status | Public Access |  | Desktop | Mobile | Current Task owner | Comments
1.1 | Unauthenticated Home Page | [8 empty] | Valerie
1.1.2 | Program Benefits Banner | Onboarding and Recruitment |  | 2025-01-17 | Placeholder copy | View Wireframes |  | New Brand | New Brand |  | Ready to Elevate you success? Empower your business with the 8x8 Elevate Partner Program. Offering your the tools, resources, and support you need to drive growth, boost revenue, and deliver outstanding value to your customers. Join now
1.1.3 | Program Elevate Banner | Onboarding and Recruitment |  | 2025-01-17 | Placeholder copy | View Wireframes |  | New Brand | New Brand |  | Changes marked up in doc supplied
1.1.4 | Program Rewards Banner | Onboarding and Recruitment |  | 2025-01-17 | Placeholder copy | View Wireframes |  | New Brand | New Brand |  | Changes marked up in doc supplied
1.2 | Partner Interest Form | Onboarding and Recruitment |  |  | Placeholder copy |  |  | New Brand | New Brand |  | No changes required
1.2.1 | Form Details | Onboarding and Recruitment |  | 2025-01-31 | Placeholder copy | View Wireframes |  | New Brand | New Brand |  | No changes required
1.2.2 | Submission Confirmation | Onboarding and Recruitment |  | 2025-01-31 | Placeholder copy | View Wireframes |  | New Brand | New Brand |  | No changes required
02 Registration/Sign-in | [7 empty] | Brand UI
Number | Page | Workstream | DRI |  | Content | Partner PRM | Partner Member | Desktop | Mobile | Current Task owner
2.1 | Email Invitation | Onboarding and Recruitment |  | 2025-01-31 | Placeholder copy | View Wireframes | View Wireframes | New Brand | New Brand | Valerie | Changes marked up in doc supplied
2.2 | Sign In | Onboarding and Recruitment |  | 2025-01-31 | Placeholder copy | View Wireframes |  | New Brand | New Brand |  | No changes required
2.3 | Initiate Password | Onboarding and Recruitment |  | 2025-01-31 | Placeholder copy | View Wireframes |  | New Brand | New Brand |  | No changes required
2.3.1 | Set New Password | Onboarding and Recruitment |  | 2025-01-31 | Placeholder copy | View Wireframes |  | New Brand | New Brand |  | No changes required
03 Authenticated Prospect Experience
Number | Page | Workstream | DRI |  | Content | Partner PRM | Partner Member | Brand UI |  | Current Task owner
3.1 | Partner 5 steps form | Onboarding and Recruitment
3.1.1 | --Step 1 - Complete Your Partner Profile | Onboarding and Recruitment |  | 2025-01-31 | Placeholder copy | View Wireframes | Not applicable | New Brand | New Brand | Patricia | Changes marked up in doc supplied
3.1.2 | --Step 2 - NDA Signature | Onboarding and Recruitment |  | 2025-01-31 | Placeholder copy | View Wireframes | Not applicable | New Brand | New Brand | Patricia | Replicate the header amends from Step 1 and duplicate across all steps. No other changes required.
3.1.3 | --Step 3 - 8x8 Partner Program Review | Onboarding and Recruitment |  | 2025-01-31 | Placeholder copy | View Wireframes | Not applicable | New Brand | New Brand | Patricia | Replicate the header amends from Step 1 and duplicate across all steps. No other changes required.
3.1.6 | --Step 4 - MSA Signature | Onboarding and Recruitment |  | 2025-01-31 | Placeholder copy | View Wireframes | Not applicable | New Brand | New Brand | Patricia | Replicate the header amends from Step 1 and duplicate across all steps. No other changes required.
3.1.7 | --Step 5 - Account Activation | Onboarding and Recruitment |  | 2025-01-31 | Placeholder copy | View Wireframes | Not applicable | New Brand | New Brand | Patricia | Replicate the header amends from Step 1 and duplicate across all steps. No other changes required.
3.1.8 | --Application Completed Confirmation | Onboarding and Recruitment |  | 2025-01-31 | Placeholder copy | View Wireframes | Not applicable | New Brand | New Brand | Patricia | Replicate the header amends from Step 1 and duplicate across all steps. No other changes required.
3.2 | Email Account Activation | Onboarding and Recruitment |  | 2025-01-31 | Placeholder copy | View Wireframes | Not applicable | New Brand | New Brand | Patricia | Changes marked up in doc supplied
3.2 | Resources | Onboarding and Recruitment |  |  |  | Under scope definition | Not applicable |  |  | Patricia
04 Authenticated Partner Experience
Number | Page | Workstream | DRI |  | Content | Partner PRM | Partner Member | Brand UI |  | Current Task owner
4.1 | Home Page Onboarding Experience - New Scope | Onboarding and Recruitment |  | 2025-01-31 | Placeholder copy | View Wireframes | View Wireframes | New Brand | New Brand | Patricia | Changes marked up in doc supplied
4.3 | My Learning Experience MVP | Onboarding and Recruitment |  | 2025-01-31 | Placeholder copy | View Wireframes | View Wireframe | New Brand | New Brand | Valerie | To be amended and supplied w/c 24th.
4.4 | My Team Experience | Onboarding and Recruitment |  |  |  |  | Not applicable | New Brand | New Brand |  | N/A
| --My Team (Zero State) | Onboarding and Recruitment |  | 2025-01-31 | Placeholder copy | View Wireframes | Not applicable | New Brand | New Brand |  | Require input from 8x8 for the bottom boxes.
| --Add New Member | Onboarding and Recruitment |  | 2025-01-31 | Placeholder copy | View Wireframes | Not applicable | New Brand | New Brand |  | No changes required.
| --My Team (Complete State) | Onboarding and Recruitment |  | 2025-01-31 | Placeholder copy | View Wireframes | Not applicable | New Brand | New Brand |  | Require input from 8x8 for the bottom boxes.
4.5 | Resources Experience | Onboarding and Recruitment | [7 empty] | Patricia | N/A
| --Resources | Onboarding and Recruitment |  | 2025-01-31 | Placeholder copy | WIP Wireframes | Under scope definition | New Brand |  | Patricia | No changes required.
| --CMS/Article/Resource Detail Template | Onboarding and Recruitment |  | 2025-01-31 | Placeholder copy | Under scope definition | Under scope definition | Updating UI |  | Patricia
4.6 | Selling Experience | Commercial
| Selling Home | Commercial |  |  | Placeholder copy | View Prototype |  | New Brand |  | June Jung | Leading to 404 page.
| --Create Cart | Commercial |  |  | Placeholder copy | WIP Wireframes |  | New Brand |  | June Jung | Please provide access to the file.
| ----Customer Information | Commercial |  |  | Placeholder copy | WIP Wireframes |  | New Brand |  | June Jung | Please provide access to the file.
| ----Digital Services Page | Commercial |  |  | Placeholder copy | WIP Wireframes |  | New Brand |  | June Jung | Please provide access to the file.
| ----Equipment Page | Commercial |  |  | Placeholder copy | WIP Wireframes |  | New Brand |  | June Jung | Please provide access to the file.
| ----Implementation & Training Page | Commercial |  |  | Placeholder copy | WIP Wireframes |  | New Brand |  | June Jung | Please provide access to the file.
| ----Review Cart Page | Commercial |  |  | Placeholder copy | WIP Wireframes |  | New Brand |  | June Jung | Please provide access to the file.
| ----Cart Submission Page | Commercial |  |  | Placeholder copy | WIP Wireframes |  | New Brand |  | June Jung | Please provide access to the file.
| --Saved Carts (List Page) | Commercial |  |  | Placeholder copy | WIP Wireframes |  | New Brand |  | June Jung | Please provide access to the file.
| --Provisioned Carts (List Page) | Commercial |  |  | Placeholder copy | WIP Wireframes |  | New Brand |  | June Jung | Please provide access to the file.
| --International DID | Commercial |  |  | Placeholder copy | WIP Wireframes |  | New Brand |  | June Jung | Please provide access to the file.
| Account Home | Commercial | [7 empty] | June Jung | Please provide access to the file.
| --Accounts (List Page) | Commercial |  |  | Placeholder copy | WIP Wireframes |  | New Brand |  | June Jung | Please provide access to the file.
| --Account Details | Commercial |  |  | Placeholder copy | WIP Wireframes |  | New Brand |  | June Jung | Please provide access to the file.
| Partner Demo | Commercial
| --Demo Request | Commercial
| --Demo Access | Commercial
| Customer POC | Commercial | [8 empty] | Removed from Scope
| --POC Request | Commercial | [8 empty] | Removed from Scope
| --POC Access | Commercial | [8 empty] | Removed from Scope
| Price Sheet Download (Resource Page) | Commercial
| Billing & Invoices | Commercial | [7 empty] | Valerie
| -- List of invoices (status: posted/paid/unpaid) | Commercial | [7 empty] | Valerie
4.7 | Reports & Dashboards | Select
4.8 | Support Experience
4.8.1 | Support Landing Page | Support and Enablement |  | 2025-01-31 | Placeholder copy | View Wireframes | View wireframe | New Brand | New Brand | Patricia | No updates required.
4.8.2 | --Topic Page | Support and Enablement |  | 2025-01-31 | Placeholder copy | View Wireframes |  | New Brand |  | Patricia | No updates required.
| --Content/CMS/Article Page | Support and Enablement |  | 2025-01-31 | Placeholder copy | View Wireframes |  | Updating UI |  | Patricia | Leading to 404 page.
| Case Deflection | Support and Enablement |  | 2025-01-31 | Placeholder copy | View Wireframes |  | Updating UI |  | Patricia | Leading to 404 page.
| Case Creation Email | Support and Enablement |  | 2025-01-31 | Placeholder copy | View Wireframes |  | New Brand | New Brand | Valerie | No updates required.
| Case Details | Support and Enablement |  | 2025-01-31 | Placeholder copy | View Wireframes |  | New Brand | New Brand | Valerie | Leading to 404 page.
| Case List | Support and Enablement |  | 2025-01-31 | Placeholder copy | View Wireframes |  | New Brand | New Brand | Valerie | No updates required.
4.9 | Profile & Account Experience | [9 empty] | Recommend increasing font size and/or the weight -as its not fully legible.Aside from this, no other changes required.
| My Profile | Onboarding and Recruitment |  |  | Placeholder copy | View Wireframes | Pending wireframe | Updating UI |  | Valerie | Recommend increasing font size and/or the weight -as its not fully legible.Aside from this, no other changes required.
| My Company (Immediate Impact Solutions) | Onboarding and Recruitment |  |  | Placeholder copy | WIP Wireframe | Pending wireframe | Updating UI |  |  | Recommend replacing top-banner with new brand imagery.
Scenario 1: Simon submits a provisioning cart for a net new customer account
Scenario 2: Simon wants to change provisioning to a submitted cart / existing customer account
Scenario 3: Simon reviews activation/deactivation actuals
Scenario 4: Simon wants to provision a POC licenses to a new customer (limit to 5, new customer only)
Scenario 5: Simon reviews the status of Provisioned Cart - Details (DS, Equip., Implementation)
Scenario 6: Simon wants to reprovsion features and reviews contextual info from the Asset View (Provisioned Assets with Activation Actuals)
Scenario 7: Priya requests a Partner Demo (org)
Note on G4: @amanda.hill@8x8.com As part of the copywriting that is needed please see wireframe links in column F which you can start to review. In our next meeting we can align on the process for you to provide that copy with @andre.malske@8x8.com . Thanks CC - @shaloo.ahluwalia@8x8.com _Assigned to amanda.hill@8x8.com_ -Muratcan Zor
Note on B59: Question to ask: Why should partner request a Demo org during onboarding? Can we auto generate and give partner a demo org and give a link access -June Jung (they/them)